## Project Planner
Phd Plan - TestifAI: A comprehensive testing framework for safe AI
[7 empty] | Month Highlight: | 36 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Research Modules | Research Questions | Ressearch Objectives | Tasks | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | MONTHS
[9 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Test case generation | How can we generate highly effective test cases that ensure complete coverage? | Efficient input sampling: Develop a sampling approach that effectively identifies and prioritizes corner cases. It can be used to guide best selection of inputs for test case generation. Effective test case generation with interpretability analysis: Implement interpretability analysis to identify and prioritize key influential features in the DNN testing process, exploring the use of high influential features for effective test case generation. | Reading Literature on Test Cases | 1 | 18 | 1 | 18 | 50%
|  |  | Exploring Libraries for Test Case Generation | 1 | 2 | 1 | 2 | 80%
|  |  | Implementing Adversarial Attacks and Semantic Adversarial test cases | 3 | 1 | 3 | 1 | 80%
|  |  | Apply the exisiting test case genrtaion methods to the benchmark datasets and analyze the results. | 13 | 1 | 0 | 0 | 0%
|  |  | Automate my proposed test generation module | 15 | 1 | 0 | 0 | 0%
Interpretablility | Can interpretability analysis aid in effective test case generation? | Effective test case generation with interpretability analysis: Implement interpretability analysis to identify and prioritize key influential features in the DNN testing process, exploring the use of high influential features for effective test case generation. | Reading liiterature on interpretabiity analysis | 4 | 24 | 4 | 24 | 30%
|  |  | Implementation of SHAP tool | 4 | 2 | 4 | 2 | 80%
|  |  | Applying SHAP to Identify Important Pixels | 4 | 3 | 4 | 6 | 70%
|  |  | Explore other interpretability analysis techniques, such as LIME, to identify key features that can guide the generation of optimal test cases for evaluating model robustness. | 15 | 3 | 0 | 0 | 0%
|  |  | Integrate Interpretability approach in test case generation module | 16 | 1 | 0 | 0 | 0%
Coverage Criteria | How can we ensure complete test coverage for deep learning models? | Systematic robustness evaluation: Integrate advanced probabilistic methods to evaluate both local coverage and global coverage , providing comprehensive error summaries and systematically assessing robustness at different levels within the framework. | Reading papers and identifying gaps | 6 | 4 | 6 | 4 | 50%
|  |  | Apply the exisiting coverage criteria to the benchmark datasets and analyze the results. | 13 | 1 | 0 | 0 | 0%
Probabilistic Programming Language | How can we systematically evaluate the robustness both at local (property- specific) and global (overall system) levels within the framework? | Systematic robustness evaluation: Integrate advanced probabilistic methodsto evaluate both local coverage and global coverage , providing comprehensive error summaries and systematically assessing robustness at different levels within the framework. | Reading Papers related to problog | 6 | 2 | 6 | 2 | 50%
|  |  | Undertsand the problog language and compiler | 9 | 1 | 9 | 1 | 80%
|  |  | Run examples on problog and try to understand inputs and outputs | 9 | 1 | 9 | 1 | 70%
Sampling | How can we sample inputs efficiently? | Efficient input sampling: Develop a sampling approach that effectively identifies and prioritizes corner cases. It can be used to guide best selection of inputs for test case generation. | Reading Papers related to sampling techniques and identify gaps | 9 | 1 | 9 | 1 | 50%
|  |  | Develop efficient sampling technique that will cover all inputs or corner cases | 10 | 2 | 0 | 0 | 0%
|  |  | Implement existing sampling techniques to identify corner cases and prioritze that corner cases | 9 | 1 | 9 | 1 | 30%
|  |  | Integrate this module into the framework | 9 | 1 | 0 | 0 | 0%
Error Summarization | How can error summarization be employed to quantify the impacts on model robustness? | Quantifying model robustness through error summarization: Innovate error summarization techniques that identify and quantify model weaknesses, utilizing error summarization to quantify the impacts on model robustness | Find ways to proper summarize the counter examples | 17 | 1 | 0 | 0 | 0%
|  |  | Best viusuals to represent erorrs report | 18 | 1 | 0 | 0 | 0%
|  |  | Integrate error summarization module in frame work | 19 | 1 | 0 | 0 | 0%
Specification | How can we clearly define and specify the properties of the system? | User-defined specifications: Formalize specifications by developing templates and a specification language that enable users to clearly define and specify the properties of the system and its associated data for testing purposes | Find a way to define specification, how to formalize it | 20 | 3 | 0 | 0 | 0%
|  |  | How to pass specifications to ProbLog | 20 | 3 | 0 | 0 | 0%
|  |  | Integrate this module into the framework | 20 | 3 | 0 | 0 | 0%
Initial Proposed Methodology | How can we design a comprehensive framework to test system robustness? | Design framework: Create a framework that test the DNN under a variety of conditions, ensuring it meets performance standards even in edge cases and adverse scenarios | Designing a conceptual framework | 8 | 4 | 8 | 4 | 70%
| How can we ensure complete test coverage for deep learning models? |  | Differentiating local and global coverage | 8 | 2 | 8 | 2 | 70%
|  |  | Implementing the Simple Adder Example | 9 | 2 | 9 | 1 | 100%
|  |  | Exploring ProbLog | 9 | 2 | 9 | 1 | 60%
|  |  | Implementing ProbLog for calculating global robustness | 9 | 2 | 9 | 1 | 80%
|  |  | Integrating ProbLog with python | 9 | 2 | 9 | 1 | 100%
|  |  | Applying the framework to different datasets | 9 | 2 | 9 | 1 | 60%
Milestones | Research Questions | Objectives | Tasks
Conference Paper 1 (EuroML Conf 2025) | How can we design a comprehensive framework to test system robustness? | Prepare and submit a paper for the International Conference | Consider publishing initial findings or presenting at a conference. | 9 | 3 | 9 | 5 | 50%
Conference Paper 2 (ICSE 2025) | Can interpretability analysis aid in effective test case generation? | Prepare and submit a paper for the International Conference | Consider publishing initial findings or presenting at a conference. | 16 | 2 | 0 | 0 | 0%
Journal Paper 1 | How can we sample inputs efficiently? How can we systematically evaluate the robustness both at local (property- specific) and global (overall system) levels within the framework? | Prepare and submit a comprehensive journal paper based on your extended research findings. | Prepare and submit a detailed manuscript based on the extended findings and analysis of the research conducted. | 19 | 4 | 0 | 0 | 0%
Journal Paper 2 | How can we clearly define and specify the properties of the system? Can interpretability analysis aid in effective test case generation? How can error summarization be employed to quantify the impacts on model robustness? | Prepare and submit a comprehensive journal paper based on your extended research findings. | Prepare and submit a detailed manuscript based on the extended findings and analysis of the research conducted. | 24 | 4 | 0 | 0 | 0%
Thesis Writing | How can we design a comprehensive framework to test system robustness? How can we clearly define and specify the properties of the system? How can we sample inputs efficiently? How can we generate highly effective test cases that ensure complete coverage? Can interpretability analysis aid in effective test case generation? How can we ensure complete test coverage for deep learning models? How can error summarization be employed to quantify the impacts on model robustness? | Prepae thesis draft | Focus primarily on writing thesis. | 24 | 3 | 0 | 0 | 0%
Thesis Submission |  | Submit thesis | Finalize and submit thesis for review. | 28 | 3 | 0 | 0 | 0%
Defense and Final Submission |  | Prepare final comments | Defense and submit the finalized thesis. | 36 | 1 | 0 | 0 | 0%